Vaidyanath Dress Rehearsal SOP

Sun May 10 - Final Pre-Pilot Validation

PharmaCare Pro v0.1.0  |  S28-F3  |  DRAFT 2026-05-09

| Field | Value |
| --- | --- |
| Owner | Sourav Shaw |
| Target window | Sunday 2026-05-10 evening (latest start 18:00 IST) |
| Total time budget | 91 minutes floor / 120 minutes ceiling |
| Pass-floor | All 13 sections complete; one P0 fail aborts; P1 captured to results template |
| VM hardware floor | 4 GB RAM / 2 vCPU / HDD (Hard Rule 4 - Playbook S3) |
| DR exit gate | Section 10 - restore from snapshot; integrity_check = ok; 500/500 products |
| Validates (does NOT replace) | A3 vaidyanath_day1_install_runbook.docx + A6 dr/runbook.docx + A6 restore_smoke_test.md |

Authority: This SOP catches bugs in a controlled VM Sunday evening so they do not surface at Vaidyanath under the owner's eye Wednesday. Where it overlaps A3 / A6, A3 / A6 win onsite. This is a validation harness, not a replacement.

# 1. Why a controlled rehearsal

Vaidyanath Day-1 is a one-shot show. Owner is watching, cashier is on the keyboard, money is moving. Surfacing a SmartScreen bug, a missing migration, a restore.ps1 hang, or a Marathi font fallback in front of the owner is fatal trust loss.

The rehearsal lets the founder catch every avoidable defect on his own machine, log it, hot-fix it overnight or at worst push to a Mon-AM patch, and arrive Monday with a dry-run he has actually performed end-to-end.

Bug found on the VM Sunday = 1 hour to fix. Same bug found at Vaidyanath Wednesday morning = pilot blocker.

# 2. Inputs to have ready before you press start

- Clone Win 11 VM (spec in Section 3); snapshotted to a clean baseline state - no PharmaCare bits, no leftover registry.

- USB image (or shared folder) containing the latest PharmaCare-Pro-Setup-v0.1.0.msi and its .sha256 sidecar.

- Copy of tools/synthetic-vaidyanath-master.csv (500 SKUs, 566 batches; A5 source-of-truth - DO NOT use the live Vaidyanath master here, this rehearsal must be repeatable).

- A printer (the same TVS-E or Epson TM-T82 that ships to Kalyan Monday). If unavailable, every print step has a PDF-fallback.

- A phone or stopwatch. Every section has a wall-clock budget. Going 1.5x over a section budget is itself a finding.

- This SOP printed (or open on a second screen). Do not drive from memory.

- Empty fill-in copy of _research_brain/06_pilot/dress_rehearsal_results_TEMPLATE.md open in a text editor.

# 3. Section 1 - Prep: VM setup (10 min)

Goal: clean Windows 11 image, blank slate, hardware floor matches the Vaidyanath rig (Hard Rule 4 perf floor: 4 GB RAM, HDD or thin-provisioned SSD).

### Steps

- Restore the cloned Win 11 VM from the clean baseline snapshot. Confirm Start menu has no PharmaCare entry.

- Allocate exactly 4 GB RAM and 2 vCPU. Do NOT over-provision - the rehearsal must reproduce the Lenovo ThinkCentre i3-8100 4-GB floor from Playbook S3.

- Disk: spinning HDD or thin-provisioned SSD (HDD-equivalent IOPS). SSD passthrough WILL hide perf regressions - banned.

- Install the printer driver (TVS-E or Epson TM-T82, same model as the shop). Print a Windows test page to confirm.

- Power-cycle the VM (Restart, not Suspend). On boot: confirm clean desktop, no leftover toast notifications, Time + Date set to IST.

Pass: clean desktop, printer driver installed and prints Win test page, RAM gauge in Task Manager shows <=2.0 GB free at idle (proves the 4-GB cap is real).

Fail / escape-hatch: RAM provisioning ignored by hypervisor -> tear down, recreate VM with the floor strictly enforced. Printer driver refuses to install on Win 11 23H2 -> switch to PDF-fallback for sections 5/6 print steps and log a P1 finding to escalate before Monday.

# 4. Section 2 - Install MSI (5 min)

Goal: mirror the SmartScreen click-through path the owner will see Monday.

### Steps

- Mount the USB image in the VM. Open PowerShell as Administrator.

- Run Get-FileHash -Algorithm SHA256 .\PharmaCare-Pro-Setup-v0.1.0.msi - compare against the .sha256 sidecar. Must match byte-for-byte.

- Double-click the MSI in Explorer. Expect SmartScreen warning - 'unrecognized app' - exactly per A3 S3.2 (DigiCert EV cert per FORWARD_PLAN_v5 S5 will not arrive until week 2; pilot ships unsigned).

- Click 'More info' -> 'Run anyway' -> UAC: Yes.

- Accept EULA. Default install path C:\Program Files\PharmaCare Pro\. Click Install. Wait ~30 sec. Click Finish.

- Start menu -> 'PharmaCare Pro' -> app launches.

Pass: main window visible. Top-right reads v0.1.0. License Activation screen shown (no license file present yet on the clean VM - this is correct).

Fail / escape-hatch: If SmartScreen has no 'More info' link, the GPO is locked-down - capture screenshot, re-run with `tauri build --debug` from apps/desktop/ to get installer logs, and pre-warn the owner that Settings > App & browser control > Reputation-based protection: off may be needed Monday. If the app crashes on launch, capture %APPDATA%\PharmaCare\logs\pharmacare-*.log, dump Sentry breadcrumbs, abort the rehearsal - this is a P0 pilot blocker.

# 5. Section 3 - First-run wizard (15 min)

Goal: drive B3's OnboardingWizard end-to-end, exactly as Vaidyanath's owner will see it Monday.

### Use these EXACT values (so results stay reproducible across rehearsal iterations)

| Field | Value |
| --- | --- |
| Shop name | Vaidyanath Pharmacy |
| Owner name | (rehearsal placeholder, e.g. 'Test Owner') |
| GSTIN | 27ABCDE1234F1Z5 (synthetic, Luhn-valid 15-char) |
| Retail-license number | MH-DRG-12345 |
| Schedule-H license number | MH-SH-67890 |
| DPO name + phone | Sourav Shaw + your hotline number |
| Grievance Officer | same as DPO (sole-prop allowed) |
| Locale | Marathi (Q-007 default per USER_INPUT_QUEUE.md) |
| Auto-IRN toggle | OFF (Q-004 default = under-2 cr turnover) |
| Owner PIN | rehearsal-only (e.g. 1111) |

### Steps

Walk all 6 wizard steps per A3 S4.1-S4.6. Type - do not paste - the GSTIN to validate the on-blur Luhn checker fires green. Drag a placeholder PDF into the retail-license upload zone. Confirm UI flips to Devanagari script after Locale step.

Pass: Dashboard loads. Top bar shows 'Vaidyanath Pharmacy'. DPDP shield top-right is GREEN. Schedule-H register tab visible.

Fail / escape-hatch: Any wizard step rejects valid input -> screenshot + cross-reference apps/desktop/src/components/OnboardingWizard.test.tsx and the validators colocated inside apps/desktop/src/components/OnboardingWizard.tsx. If the locale step does not flip the UI to Marathi, log P0 against packages/design-system/src/i18n/mr.ts (D4 i18n migration) and switch to Hindi to continue the rehearsal.

# 6. Section 4 - Marg CSV import (10 min)

Goal: prove the importer ingests 500 SKUs cleanly with the synthetic master file.

### Steps

- Copy tools/synthetic-vaidyanath-master.csv from the host into a staging folder on the VM (e.g. C:\ProgramData\PharmaCare\import-staging\master.csv).

- In-app: Settings -> Data -> Import -> Marg CSV -> Master.

- Run Dry-run first. Wait. Confirm the importer summary screen shows: 500 products parsed, 566 batches, 34 expired flagged, 0 missing-GST, 0 Schedule-H without licence-class.

- If dry-run is clean, click Live Import. Wait. Confirm the post-import summary matches dry-run counts exactly.

- Spot-check 5 SKUs by name: Crocin 500, Dolo 650, Allegra 120, Pantop 40, Telma 40 - each should be findable via search.

Pass: 500 / 566 / 34 / 0 / 0 numbers match exactly. All 5 spot-checks return rows. Importer log file in %APPDATA%\PharmaCare\logs\ has 0 ERROR lines.

Fail / escape-hatch: Any count mismatch -> capture importer log + the dry-run JSON and cross-reference packages/migration-import/CHANGELOG.md and packages/migration-import/__tests__/. If the importer hangs on a single row, kill the import, read the log to find the offending SKU, log P0. The synthetic master is the source-of-truth - a row that breaks here will break the live Vaidyanath master Tuesday.

# 7. Section 5 - Test bill: OTC (5 min)

Goal: save a single non-Schedule-H bill end-to-end including print + drawer.

### Steps

- F2 (or click 'New Bill'). Search 'Crocin 500' - pick the first OTC SKU returned.

- Quantity 1. Tender = Cash. Amount: enter exact bill total. Press Enter.

- Bill saves. Receipt prints. Drawer pulse fires (audible click within 200 ms).

Pass: bill number VP-2026-05-13-0001 (or current-date variant) saved. Receipt header shows shop name + GSTIN + Marathi date. Footer reads 'IRN: skipped' (under-2 cr default per Q-004). Drawer pop within 200 ms.

Fail / escape-hatch: No printer? Switch the printer dropdown to 'Save as PDF' - the receipt should write to %APPDATA%\PharmaCare\receipts\ and the bill saves regardless. No drawer? Skip the pulse and continue - log as P2 (drawer wiring is a Day-1 onsite task, not a rehearsal blocker). Bill SAVE fails -> P0, capture log.

# 8. Section 6 - Test bill: Schedule-H (10 min)

Goal: prove S28-A1 + D1 counseling-gate fires AND clears.

### Steps

- F2 (new bill). Search the first Schedule-H drug from the synthetic master (e.g. Augmentin 625, or the first H-class row in synthetic-vaidyanath-master.csv - confirm the H badge renders next to the SKU name).

- Quantity 1. Press Enter to attempt save WITHOUT counseling.

- Expect: COUNSELING_INCOMPLETE red banner fires, save blocked, CounselingScreen modal opens.

- Fill counseling form: patient name, doctor name, prescription date, counsel-given checkbox.

- Click 'Confirm Counseling'. Modal closes.

- Re-press Enter to save the bill. Bill saves.

- Open Schedule-H register tab. Confirm a new row appears matching the bill.

Pass: Banner fires on first attempt; modal opens and is required (cannot dismiss without filling); after counseling, save succeeds; register has the new row.

Fail / escape-hatch: Banner does not fire -> P0, the save_bill counseling gate is broken. Cross-reference apps/desktop/src/components/BillingScreen.tsx (S28-D1 wire-up) and apps/desktop/src-tauri/tests/counseling_integration_test.rs. Modal opens but cannot be dismissed even after filling -> P0, log of checkCounselingCompleteRpc round-trip needed. Register row missing -> P1, the migration 0050 may not have run.

# 9. Section 7 - Test return (5 min)

Goal: end-to-end partial-quantity refund on the Schedule-H bill from Section 8.

### Steps

- Navigate Returns -> New Return.

- Lookup by bill number (the Section 8 Schedule-H bill).

- Select the line. Quantity to refund: 1 (full qty since we sold 1 in Section 8 - or partial if you sold >1).

- Tender = Cash. Submit.

- Return saved. Cash refund total appears on screen.

Pass: return record saved. Cash refund recorded in the daybook. Stock for the SKU returns to its pre-bill level.

Fail / escape-hatch: Lookup misses the bill -> P1, search index broken; capture and log. Refund total wrong -> P0, the partial-refund A8 logic regressed; cross-reference CURRENT_SPRINT_STATE.md 'S28 ship summary' for the partial-refund tests and re-run them.

# 10. Section 8 - GSTR-3B export (5 min)

Goal: prove the report-export round-trips to a valid file.

### Steps

- Reports -> Compliance -> GSTR-3B.

- Period: current month.

- Click Export -> choose folder (e.g. C:\PCP-Rehearsal\exports\).

- Wait for 'Export complete' toast.

- Open the file. Inspect: must be valid JSON (or whichever format the build emits - Excel/PDF acceptable). Top-level fields present; no nulls in mandatory fields.

Pass: file written, openable, well-formed, contains the Section 7 + Section 8 bills.

Fail / escape-hatch: Export hangs -> P1, capture the Tauri log. File invalid -> P1, cross-reference apps/desktop/src/components/ReportsExportPanel.tsx and apps/desktop/src-tauri/src/reports/. Not a pilot-blocker (owner does not file GSTR-3B Day-1) but ship a hotfix Tuesday.

# 11. Section 9 - Snapshot (3 min)

Goal: prove the backup script round-trips a .tar.zst + .sha256 sidecar.

### Steps

- Settings -> Backup -> Take Snapshot Now (or run scripts/dr/snapshot.ps1 from PowerShell).

- Choose target: external folder (e.g. D:\PharmacareBackups\).

- Wait for 'Snapshot complete' toast.

- Open the target folder in Explorer. Confirm two files: pharmacare-snapshot-2026-05-10-<timestamp>.tar.zst AND pharmacare-snapshot-2026-05-10-<timestamp>.tar.zst.sha256.

- Get-FileHash -Algorithm SHA256 <tar.zst> - must match the contents of the .sha256 sidecar.

Pass: both files present, sha256 matches. tar.zst is >=200 KB.

Fail / escape-hatch: Snapshot hangs -> P0, the DR backbone is broken; abort and triage immediately. sha256 mismatch -> P0, snapshot is corrupt; triage A6 scripts/dr/snapshot.ps1.

# 12. Section 10 - Restore from snapshot (10 min) - DR EXIT GATE

Goal: the Section 11 snapshot restores cleanly to a working app. THIS IS A HARD-FAIL GATE - failure here aborts the pilot.

### Steps

- Quit the app from system tray.

- Rename %APPDATA%\PharmaCare\pharmacy.sqlite -> pharmacy.sqlite.broken. Touch a 0-byte pharmacy.sqlite to simulate corruption (per A6 restore_smoke_test.md P1 path).

- PowerShell (admin): .\scripts\dr\restore.ps1 -Source <path-to-snapshot.tar.zst>

- Watch console output. Wait for 'Restore complete'.

- Relaunch the app. Sign in as the owner.

- Settings -> Diagnostics -> Integrity Check. Expect: 'ok'.

- Search products: confirm all 500 SKUs from Section 6 are present.

- Open the Section 7 OTC bill and the Section 8 Schedule-H bill. Confirm both load with totals matching what was saved.

- Open Schedule-H register. Confirm the Section 8 counsel-log row is present.

- Run PRAGMA integrity_check via Diagnostics. Expect: 'ok' (single line).

Pass: integrity_check = 'ok'; all 500 products present; both bills load correctly with original totals; counsel-log row present.

Fail / escape-hatch - HARD-FAIL - pilot blocked: Capture: full restore.ps1 console transcript, the rotated logs in %APPDATA%\PharmaCare\logs\, the snapshot file, and the pharmacy.sqlite.broken file. Open a P0 issue with label dr-drill-fail per A6 restore_smoke_test.md. Page Sourav (you). Treat May 13 as blocked until the regression is closed and a fresh rehearsal passes Section 10. Do not drive to Kalyan with Section 10 unresolved.

# 13. Section 11 - Locale switch (3 min)

Goal: prove Marathi <-> Hindi flip works at runtime without restart.

### Steps

- Settings -> Language -> Hindi. Confirm prompt; click Apply.

- UI re-renders in Devanagari. Spot-check the Billing menu, Returns menu, Reports menu - strings differ from Marathi.

- Confirm 5 specific keys flip per packages/design-system/src/i18n/hi.ts vs packages/design-system/src/i18n/mr.ts - pick: bill.new, bill.save, returns.title, reports.title, settings.language.

- Switch back: Settings -> Language -> Marathi -> Apply.

- Confirm UI returns to Marathi strings.

Pass: both flips happen without app restart; both dictionaries land correct strings on the 5 spot-check keys.

Fail / escape-hatch: Restart required -> P1, Settings.tsx locale-switch handler missing live re-render. Wrong strings or English fallthrough on a key -> P1, fill in packages/design-system/src/i18n/<locale>.ts; not pilot-blocking unless the missing key is in the Day-1 Billing flow.

# 14. Section 12 - Performance smoke (5 min)

Goal: measure cold-start and p95 bill-save on the 4-GB / HDD floor. Per PROJECT_INSTRUCTIONS S10 these are GA gates, not pilot gates - but a 5x miss tells us something.

### Steps

- Quit the app.

- PowerShell: .\scripts\perf\run-perf.ps1 (if available; otherwise the app's Settings -> Diagnostics -> 'Run perf smoke' button).

- Capture: cold-start time (app launch -> Dashboard interactive), p95 bill-save (10 sample saves), search latency (10 sample searches against the 500-SKU master).

Pass: cold-start <3.0 s, p95 bill-save <400 ms, search p95 <200 ms (per Playbook S3 hardware floor + PROJECT_INSTRUCTIONS S10).

Fail / escape-hatch: Any number 1.0-1.5x over -> log P2, NOT pilot-blocking; capture for S29 perf sprint. Any number >2x over -> log P1, escalate; the rehearsal continues but the founder must arrive at Vaidyanath knowing the rig may feel slow.

# 15. Section 13 - Tear-down (5 min)

Goal: clean exit + off-site backup of the rehearsal artefacts.

### Steps

- Uninstall PharmaCare Pro from Settings -> Apps & features.

- Delete %APPDATA%\PharmaCare\. Delete C:\ProgramData\PharmaCare\.

- Copy the Section 11 snapshot folder from the VM to a host-side off-site backup location (e.g. external SSD, cloud bucket).

- Take a final VM snapshot named post-rehearsal-2026-05-10. This is your 'we know this works' baseline.

- Fill in the last column of dress_rehearsal_results.md per Section 16 below and commit.

Pass: uninstall completes; data dirs gone; off-site backup present; results template saved.

# 16. Capture results

After the rehearsal, fill in the per-section pass/fail table in _research_brain/06_pilot/dress_rehearsal_results.md (created from dress_rehearsal_results_TEMPLATE.md). Commit the filled file before bed Sunday - this is the artefact you will cite Monday morning if anything looks weird onsite.

# 17. Total time + abort policy

| Section | Budget (min) | Cumulative (min) |
| --- | --- | --- |
| 1 Prep | 10 | 10 |
| 2 Install MSI | 5 | 15 |
| 3 First-run wizard | 15 | 30 |
| 4 Marg CSV import | 10 | 40 |
| 5 OTC bill | 5 | 45 |
| 6 Schedule-H bill | 10 | 55 |
| 7 Return | 5 | 60 |
| 8 GSTR-3B export | 5 | 65 |
| 9 Snapshot | 3 | 68 |
| 10 Restore (DR exit gate) | 10 | 78 |
| 11 Locale switch | 3 | 81 |
| 12 Performance smoke | 5 | 86 |
| 13 Tear-down | 5 | 91 |

Floor: 91 min. Ceiling: 120 min (allows 30 min of escape-hatch / triage).

### Abort policy

- P0 in Sections 2, 3, 6, 10, 11 (MSI, wizard, Sched-H, snapshot, restore): STOP THE REHEARSAL, fix, restart from Section 1.

- P1: log to results template, continue.

- P2: log, continue, schedule for S29.

If the rehearsal does not complete a full clean pass by 21:00 IST Sunday, the pilot is reschedule territory - call the owner. Better to push by 48 h than to install broken software.

# 18. Cross-reference index

| Reference | Path | Why |
| --- | --- | --- |
| A1 (counseling) | apps/desktop/src/components/CounselingScreen.tsx + migration 0050 | Section 8 expects this to fire |
| A3 (Day-1 runbook) | pharmacare-pro/docs/pilot/vaidyanath_day1_install_runbook.docx | This SOP validates A3's S3-S9 onsite path |
| A5 (synthetic data) | tools/synthetic-vaidyanath-master.csv | Section 6's input |
| A6 (DR runbook + scripts) | pharmacare-pro/docs/dr/runbook.docx + scripts/dr/{snapshot,restore}.ps1 + restore_smoke_test.md | Sections 11 + 12 - extends placeholder |
| B2 (i18n) | packages/design-system/src/i18n/{en,hi,mr}.ts | Section 13 spot-check source |
| B3 (onboarding) | apps/desktop/src/components/OnboardingWizard*.tsx + migration 0052 | Section 5's wizard |
| D1 (counseling wire-up) | apps/desktop/src/components/BillingScreen.tsx | Section 8's COUNSELING_INCOMPLETE banner |
| Q-004 / Q-007 | _research_brain/00_session_state/USER_INPUT_QUEUE.md | Section 5 default values |
| Hard Rule 4 | Playbook v2.0 S3 hardware floor | Section 3 RAM/HDD spec |
| FORWARD_PLAN_v5 S3 | _research_brain/99_forward_plan/FORWARD_PLAN_v5_2026-05-08.md | Day 2 Sun May 10 dress rehearsal mention |

End of Vaidyanath Dress Rehearsal SOP - S28-F3 - DRAFT 2026-05-09